## Sheet1
Trimester | Academic Week | Week Start Date | ENGR 489 Deliverables Due | Self-Imposed Deadlines | Project Stages Guide
T1 | Wk 3 | 2018-03-19 |  |  | Initiation
T1 | Wk 4 / Easter | 2018-03-26 | Project Proposal |  | Planning
T1 | Wk 4 / Easter | 2018-04-02 |  |  | Planning
T1 | Wk 5 | 2018-04-09 |  |  | Planning
T1 | Wk 6 | 2018-04-16 |  |  | Planning
T1 | Mid tri break | 2018-04-23 |  |  | Planning
T1 | Wk 7 | 2018-04-30 |  |  | Planning
T1 | Wk 8 | 2018-05-07 |  |  | Planning
T1 | Wk 9 | 2018-05-14 |  | Draft Preliminary Report | Planning
T1 | Wk 10 | 2018-05-21 |  |  | Execution
T1 | Wk 11 | 2018-05-28 |  |  | Execution
T1 | Wk 12 | 2018-06-04 | Preliminary Report |  | Execution
T1 | Exam Period | 2018-06-11 |  |  | Execution
T1 | Exam Period | 2018-06-18 |  |  | Execution
T1 | Exam Period | 2018-06-25 |  |  | Execution
T1 | Exam Period | 2018-07-02 |  |  | Execution
| Mid year break | 2018-07-09 |  |  | Execution
T2 | Wk 1 | 2018-07-16 | 10 min Presentation |  | Execution
T2 | Wk 2 | 2018-07-23 |  |  | Execution
T2 | Wk 3 | 2018-07-30 |  |  | Execution
T2 | Wk 4 | 2018-08-06 |  |  | Execution
T2 | Wk 5 | 2018-08-13 |  |  | Execution
T2 | Wk 6 | 2018-08-20 |  |  | Execution
T2 | Mid Tri break | 2018-08-27 |  |  | Execution
T2 | Mid tri break | 2018-09-03 |  |  | Execution
T2 | Wk 7 | 2018-09-10 |  |  | Execution
T2 | Wk 8 | 2018-09-17 |  |  | Execution
T2 | Wk 9 | 2018-09-24 |  | Draft Final Report | Execution
T2 | Wk 10 | 2018-10-01 | Project Snapshot |  | Execution
T2 | Wk 11 | 2018-10-08 |  |  | Execution
T2 | Wk 12 | 2018-10-15 | Final Report |  | Closing
T2 | Exam Period | 2018-10-22
T2 | Exam Period | 2018-10-29
T2 | Exam Period | 2018-11-05
T2 | Exam Period | 2018-11-12 | 10 min Presentation